10/21/14

IM Meeting canceled today, due to minimal updates.

1. Schedule update from Tu-Anh

* How are GNR, BQS moving through production – go live date?
  + Per Lee Ann: C. Chi will start coding the assessments, so still tracking to 1/2015 go live date.
* CPL
  + Eric working on edit: 10/16-10/29
  + Tu-Anh completed art manuscript
  + Warner will receive reviews when Eric sends him edit

1. Art review coordinated by Tu-Anh:

* Authors and Jane approved latest BQS art batch
* Authors and Jane working on GNR art batch

Still pending:

1. Tu-Anh: ABP batched schedule (art and interactives) to be incorporated into our development schedule

* Please schedule time for Eric to look at the animations/interactives alpha prototypes

1. Serina’s talk with Mark (re: ARP draft02) postponed until 10/27. Mark has received reviewer feedback (only R6, R7 – strongest reviews in line with Eric’s feedback).
2. Once Serina has discussion with Mark, we will kick-off topic 5 with Warner as the lead author.